## Sheet1
Chapter | Topic | Initiatives | AUG | [16 empty] | SEPT | [18 empty] | OCT
|  |  | SPRINT 1 | [7 empty] | SPRINT 2 | [8 empty] | SPRINT 3 | [8 empty] | SPRINT 4
|  |  | WEEK 1 |  |  |  |  | WEEK 2 |  |  | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  | WEEK 1 |  |  |  |  | WEEK 2
|  |  | 7 | 8 | 9 | 10 | 11 | 14 | 15 | 16 | 21 | 22 | 23 | 24 | 25 | 28 | 29 | 30 | 31 | 4 | 5 | 6 | 7 | 8 | 11 | 12 | 13 | 14 | 18 | 19 | 20 | 21 | 22 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2
6 | 1. Git flow - Memahami Konsep Version Control 2. GIT Flow CLI & GUI | Sprint Planning | bar: WEEK 1 7
1. Compile test case for automation | bar: WEEK 1 8
2. Create Gherkin script test | bar: WEEK 1 10
Sprint Review | bar: WEEK 2 16
7 | 1. Katalon Automation intro - POM 2. Katalon Automation Intro - Selenium Intro 3. Katalon Automation Intro - Katalon Intro 4. Web automation testing | Sprint Planning | bar: WEEK 1 21
1. Finish & revision Gherkin script test | bar: WEEK 1 22
2. Map element/selector for web automation test | bar: WEEK 1 24
Sprint Review | bar: WEEK 2 31
8 | 1. Web automation testing 2. Web automation reporting 3. Android automation testing | Sprint Planning | bar: WEEK 1 4
1. [DONE] Map element for web automation test | bar: WEEK 1 5
2. [DONE] Web automation test development | bar: WEEK 2 11
3. [START] Map element for android automation test | bar: WEEK 2 13
Sprint Review | bar: WEEK 2 14
9 | 1. Android automation testing 2. Android automation reporting | Sprint Planning | bar: WEEK 1 18
1. Map element for android automation test | bar: WEEK 1 19
2. Android automation test development | bar: WEEK 2 25
Sprint Review | bar: WEEK 2 28
Challenge Submission Deadline | bar: WEEK 2 2
Notes:
1. Initatives adalah hal yang perlu dikerjakan di setiap sprint
2. Per-team dapat melakukan perubahan initative yang akan dikerjakan setiap sprint, setiap team bebas menentukan hal apa saja yang akan mereka kerjakan setiap sprint. Contoh: Tim A pada Sprint 1 hanya akan mengerjakan point 1. Compile test case for automation. Akan tetapi hal yang tidak dikerjakan pada Sprint 1, berpengaruh ke goals sprint 2, dan begitu seterusnya
3. Setiap initiatives akan di-breakdown lagi dalam bentuk ticket-ticket yang akan di-assign ke setiap tim member. Dapat menggunakan Trello, Clickup, atau Jira sebagain ticket managementnya
4. Semua ticket yang telah di-commit untuk dikerjakan di setiap sprint harus selesai di sprint tersebut, jika tidak selesai maka akan di-carry over ke sprint selanjutnya